📌 Project Milestones Document

Project: Basic Inventory Management System

Tech Stack: Django + React

1️⃣ Project Overview

Objective

To develop a web-based Inventory Management System that allows businesses to:

- Manage products

- Track stock levels

- Monitor suppliers

- Record sales and purchases

- Generate basic reports

Scope

The system will:

- Provide authentication and role-based access

- Allow CRUD operations for inventory entities

- Maintain real-time stock updates

- Provide dashboard analytics

2️⃣ Development Methodology

Model: Agile (Sprint-based)
Sprint Duration: 1–2 weeks
Total Duration: 6–8 weeks

3️⃣ Milestones Breakdown

🟢 Milestone 1: Project Setup & Architecture Design

Duration: Week 1

Objectives

- Define system architecture

- Setup development environment

- Initialize backend and frontend projects

Backend Tasks (Django)

- Create Django project

- Setup virtual environment

- Install:

  - Django

  - Django REST Framework

  - PostgreSQL driver (psycopg2)

- Configure database

- Setup CORS

- Create base app structure

Frontend Tasks (React)

- Initialize React project (Vite recommended)

- Setup folder structure

- Install:

  - Axios

  - React Router

  - UI framework (e.g., MUI / Tailwind)

- Configure API base URL

Deliverables

- Running backend server

- Running frontend app

- Git repository initialized

🟢 Milestone 2: Database Design & Core Models

Duration: Week 2

Objectives

Design and implement core database schema.

Core Entities

| Entity | Description |
| --- | --- |
| User | System users (Admin, Staff) |
| Product | Item details |
| Category | Product classification |
| Supplier | Vendor information |
| Stock | Quantity tracking |
| Purchase | Incoming stock |
| Sale | Outgoing stock |

Backend Tasks

- Create Django models

- Define relationships (ForeignKey, OneToOne)

- Create migrations

- Implement Django Admin customization

Deliverables

- ER Diagram

- Database schema finalized

- Admin panel functional

🟢 Milestone 3: Authentication & Authorization

Duration: Week 3

Objectives

Implement secure login system.

Backend Tasks

- JWT authentication using DRF

- Role-based permissions

- User registration & login APIs

Frontend Tasks

- Login page

- Token storage

- Protected routes

- Logout functionality

Deliverables

- Secure authentication flow

- Role-based route protection

🟢 Milestone 4: Product & Inventory Management

Duration: Week 4

Objectives

Implement CRUD functionality.

Backend APIs

- Create Product

- Update Product

- Delete Product

- Get Product List

- Stock Update API

Frontend Pages

- Product List

- Add Product Form

- Edit Product Page

- Delete confirmation

- Stock display indicator (Low stock alert)

Deliverables

- Fully functional product management

- API tested with Postman

🟢 Milestone 5: Purchase & Sales Module

Duration: Week 5

Objectives

Implement stock flow logic.

Backend Tasks

- Purchase model + API

- Sale model + API

- Auto stock increment/decrement logic

- Transaction validation

Frontend Tasks

- Add Purchase Page

- Add Sale Page

- View transaction history

Deliverables

- Stock auto-updates on purchase/sale

- Error handling for insufficient stock

🟢 Milestone 6: Dashboard & Reporting

Duration: Week 6

Objectives

Create visual analytics.

Backend

- Summary APIs:

  - Total products

  - Total sales

  - Low stock items

  - Monthly sales

Frontend

- Dashboard page

- Charts (Recharts / Chart.js)

- Summary cards

- Filters (Date range)

Deliverables

- Functional dashboard

- Basic reporting features

🟢 Milestone 7: Testing & Optimization

Duration: Week 7

Backend

- Unit testing (Django TestCase)

- API validation

- Performance optimization

- Error handling improvements

Frontend

- UI testing

- Form validation

- Error boundary handling

Deliverables

- Tested application

- Bug report document

🟢 Milestone 8: Deployment

Duration: Week 8

Backend Deployment Options

- Heroku

- Render

- Railway

Frontend Deployment Options

- Vercel

- Netlify

Tasks

- Configure environment variables

- Setup production database

- Enable HTTPS

- Final build & deployment

Deliverables

- Live production URL

- Deployment documentation

4️⃣ Risk Management

| Risk | Mitigation |
| --- | --- |
| API integration issues | Use Swagger for testing |
| Authentication bugs | Use tested JWT packages |
| Data inconsistency | Use atomic transactions |
| Deployment errors | Staging environment testing |

5️⃣ Success Criteria

- Users can manage inventory without manual calculations

- Stock updates automatically

- System prevents negative stock

- Dashboard provides accurate reports

- Secure login system

6️⃣ Future Enhancements (Phase 2)

- Barcode scanning

- Multi-warehouse support

- Export to Excel/PDF

- Email alerts for low stock

- Role-based granular permissions

- Audit logs